## 00 ¦ Case Study
FICTIONAL ILLUSTRATIVE CASE STUDY — SELF-INITIATED WORK SAMPLE — NOT A REAL EVENT, QUOTE, OR CLIENT ENGAGEMENT
CASCADE BRIDGE PROGRAM
Seattle Executive Delegation Visit ¦ Illustrative Program Management Work Sample
A fictional, self-initiated 3-day program designed to demonstrate executive hospitality strategy, event operations, vendor management, budgeting, and guest experience controls.
| PROGRAM PROFILE |  | FINANCIAL CONTROL | GUEST EXPERIENCE
| Scope Fictional international executive delegation Seattle, Washington July 16–18, 2026 |  | Estimated Budget $335,550 planned spend 11 workstreams 14 fictional vendors | Portfolio Use Demonstrates planning rigor only. No real VIP, sponsor, public body, vendor, or sports organization is represented.
Portfolio Framing
How to discuss this sample honestly in a job application or portfolio.
| What this is | A self-initiated, fictional planning sample built to demonstrate how Gale structures executive hospitality programs.
| What this is not | It is not a real FIFA, royal, government, sporting-body, or client engagement. Vendor names, costs, contacts, guest counts, dates, and operational details are invented.
| What it demonstrates | Strategic framing, program architecture, financial control, vendor coordination, guest journey thinking, delivery governance, and decision management.
| Use in portfolio | Label it “Illustrative Seattle Executive Delegation Case Study” and be prepared to explain the planning rationale, tradeoffs, and control structure in an interview.
Workbook contents
01 Executive Summary
02 Brand System
03 Guest Itinerary
04 Master Budget
05 Budget Dashboard
06 Vendor Directory
07 Master Timeline
08 Run of Show
09 RACI & Workstreams
10 Guest Matrix
11 Risk & Decisions
12 Comms Cadence

## 01 ¦ Executive Summary
FICTIONAL ILLUSTRATIVE CASE STUDY — SELF-INITIATED WORK SAMPLE — NOT A REAL EVENT, QUOTE, OR CLIENT ENGAGEMENT
Executive Summary
Program: Cascadia Bridge Program ¦ Example dates: July 16–18, 2026 ¦ City: Seattle, WA
| PROGRAM INTENT Create a highly hosted Seattle visit that advances senior stakeholder relationships, provides confident local orientation, and demonstrates disciplined delivery at every guest touchpoint. |  |  | PRIMARY AUDIENCES Fictional delegation principals, executive hosts, strategic partners, accompanying family members, and a small internal leadership team. |  | SUCCESS SIGNALS Every guest is expected, every transition has an owner, executive time is protected, local moments feel personal, and the final readout identifies next-step relationship opportunities.
Leadership Dashboard
Illustrative program-level controls for a senior steering group.
| DELEGATION FOOTPRINT |  | WORKING BUDGET |  | CRITICAL DECISIONS | PROGRAM DAYS | WORKSTREAMS
| 32 guests |  | $326,250 |  | 11 open / closed gates | 3 full days | 11 coordinated streams
Delivery Principles
The operating rules that keep a complex executive program coherent.
| 01 | Relationship first | Every format, room, guest list, and host touchpoint is tied to a specific relationship opportunity.
| 02 | One source of truth | The workbook is the control center; every owner updates status, decision needs, and dependencies in one place.
| 03 | White-glove without theatre | Personalization is operationally feasible, discreet, and useful rather than decorative.
| 04 | Seattle has a role | Water, weather, neighborhood texture, and transitions shape the guest journey and the contingency plan.
| 05 | Read the room after | A structured post-program readout captures relationship signals, friction points, and recommended next steps.

## 02 ¦ Brand System
FICTIONAL ILLUSTRATIVE CASE STUDY — SELF-INITIATED WORK SAMPLE — NOT A REAL EVENT, QUOTE, OR CLIENT ENGAGEMENT
Brand System
Fictional program identity for a Seattle executive-delegation planning sample.
| CASCADE BRIDGE PROGRAM |  |  | IDENTITY CONCEPT A fictional program identity built around the idea of a well-held crossing: international guests arrive, Seattle becomes legible, and senior relationships move forward. Use the standalone original visual mark only as an illustrative concept; it is not a real organizational logo. Generated mark concept: /manus-storage/cascadia-delegation-mark_1bbd968b.png
Palette & Material Language
Color is used as an operational signal as much as a visual choice.
|  | Deep Ink | #10283F | Primary navigation, night protocol, executive decision points
|  | Ceremonial Cobalt | #1E5D8A | Schedule control, guest information, waterfront relevance
|  | Copper Thread | #B76E46 | Program moments, signatures, fine rules, host cues
|  | Warm Paper | #F7F1E6 | Primary document field, stationery, guest materials
|  | Seattle Sky | #DCE9ED | Daytime hosting, water, transition bands
|  | Evergreen | #315B50 | Local grounding, contingency, quiet depth
|  | Protocol Red | #A8373F | Primary callouts, priority gates, exception markers
Voice & Presentation Rules
How the fictional program should sound in attendee-facing and internal materials.
| Voice | Calm, exact, welcoming, discreet. Avoid inflated luxury words. Name the next useful decision.
| Typography | A confident high-contrast serif for headlines; a humanist sans for body copy; a mono face for schedules, notes, and control data.
| Guest materials | Use generous warm-paper fields, a cobalt schedule rail, small copper dividers, and only one red priority signal per page.
| Photography | Seattle water, thresholds, room preparation, florals, hands at work, confident transitions. Never imply a real VIP or official event.

## 03 ¦ Guest Itinerary
FICTIONAL ILLUSTRATIVE CASE STUDY — SELF-INITIATED WORK SAMPLE — NOT A REAL EVENT, QUOTE, OR CLIENT ENGAGEMENT
Guest Itinerary
Illustrative three-day guest journey. Locations and formats are conceptual Seattle planning examples.
Day | Date | Time | Program Moment | Conceptual Seattle Setting | Audience | Executive Host | Guest Experience Objective | Dependencies | Owner | Status
Day 1 | Jul 16 | 10:30–12:00 | Airport-to-city arrival protocol | Seattle airport arrival corridor (conceptual) | Principals + close support | Delegation lead | Make arrival calm, briefed, and seamlessly paced | Flight confirmation, luggage protocol, vehicle order | Guest Services | In progress
Day 1 | Jul 16 | 12:45–14:15 | Private Seattle welcome lunch | Waterfront private dining room (conceptual) | Principals + Seattle hosts | Executive host A | Create a warm first conversation with local context | Room set, dietary cards, seating, welcome remarks | F&B / Host | In progress
Day 1 | Jul 16 | 15:00–16:15 | Waterfront orientation drive | Seattle waterfront + civic landmarks | Full delegation | Guest host | Give the city a point of view without over-programming | Route timing, weather plan, vehicles, guide notes | Transport | Not started
Day 1 | Jul 16 | 18:30–21:30 | Opening salon dinner | Private club-style room (fictional) | Priority principals + invited partners | Executive host B | Set relationship tone through a small, intentional table | Guest hierarchy, seating, remarks, service sequence | Program Lead | In progress
Day 2 | Jul 17 | 08:00–09:00 | Executive breakfast briefing | Hotel library salon (conceptual) | Principals + internal hosts | Chief host | Align on day agenda, relationships, and decision points | Briefing books, security sweep, room set | Executive Office | Complete
Day 2 | Jul 17 | 10:00–11:30 | Innovation roundtable | Seattle innovation studio (fictional) | Delegation + senior partners | Program sponsor | Surface partnership themes in a focused room | Agenda, participant notes, moderator prep | Content | In progress
Day 2 | Jul 17 | 12:15–13:30 | Hosted market lunch | Private chef studio (fictional) | Priority guests | Executive host A | Show Seattle through seasonal hosting and relaxed conversation | Menus, transport, privacy plan, table assignments | F&B / Host | In progress
Day 2 | Jul 17 | 14:30–16:00 | One-to-one relationship windows | Hotel suite meetings | Selected principals | Assigned executives | Protect priority conversations and clear transitions | Meeting grid, rooming, escorts, timing locks | Executive Office | At risk
Day 2 | Jul 17 | 17:30–19:00 | Water / design moment | Private waterfront terrace (conceptual) | Full delegation | Guest host | Create a memorable local pause before evening program | Weather backup, floral, music level, transport | Experience Design | Not started
Day 2 | Jul 17 | 19:30–22:30 | Signature hosted dinner | Historic Seattle venue (fictional) | Principals + strategic partners | Program sponsor | Advance key relationships in a gracious, structured dinner | Seating, protocol, speaking order, security, photo plan | Program Lead | In progress
Day 3 | Jul 18 | 09:30–10:30 | Seattle neighborhood welcome | Residential / cultural orientation route | Family members + selected guests | Local host | Make personal Seattle options feel relevant and accessible | Route, accessibility, weather, family needs | Guest Services | Not started
Day 3 | Jul 18 | 11:30–12:30 | Partnership synthesis brunch | Private garden room (conceptual) | Senior delegates + hosts | Executive host B | Turn experience into clear relationship follow-through | Readout prompts, note capture, next-step owners | Program Lead | Not started
Day 3 | Jul 18 | 14:30–16:00 | Departure protocol | Hotel-to-airport corridor (conceptual) | Delegation | Guest Services lead | Close with certainty, warmth, and no loose ends | Flight reconfirmation, luggage, gifts, vehicle order | Guest Services | Not started

## 04 ¦ Master Budget
FICTIONAL ILLUSTRATIVE CASE STUDY — SELF-INITIATED WORK SAMPLE — NOT A REAL EVENT, QUOTE, OR CLIENT ENGAGEMENT
Master Budget
All amounts are fictional planning assumptions in USD. They are not quotes, real pricing, or vendor commitments.
Budget control rule: no scope, guest-count, or production change proceeds without an owner, a decision date, and a recorded financial consequence.
ID | Category | Line Item | Owner | Plan | Reforecast | Committed | Actual | Variance to Plan | Status | Decision / Notes
B-01 | Guest Services | Arrival desks, host staffing, guest communications | Guest Services | 18000 | 19500 | 8500 | 0 |  | In progress | Final host roster due Jul 2
B-02 | Guest Services | Welcome materials, local guide, gifts, room drops | Guest Services | 12750 | 14000 | 4500 | 0 |  | In progress | Select gift concept by Jun 20
B-03 | Venue & F&B | Private welcome lunch | F&B Lead | 18500 | 19800 | 19800 | 0 |  | Committed | Dietary lock Jun 30
B-04 | Venue & F&B | Signature hosted dinner | F&B Lead | 39250 | 42800 | 21400 | 0 |  | In progress | Seating change may affect format
B-05 | Venue & F&B | Executive breakfast / brunch | F&B Lead | 11600 | 10900 | 5400 | 0 |  | In progress | Room confirmation pending
B-06 | Accommodation | Hospitality suites and day-use meeting rooms | Hotel Lead | 52500 | 52500 | 52500 | 0 |  | Committed | No further change expected
B-07 | Transport | Executive SUVs, sprinters, standby vehicle | Transport Lead | 28300 | 31200 | 16200 | 0 |  | In progress | Weather backup vehicle held
B-08 | Experience Design | Florals, tablescape, arrival moments, guest materials | Experience Design | 24400 | 25800 | 7600 | 0 |  | In progress | Confirm seasonal floral substitution
B-09 | Content & Production | Briefing books, signage, discreet photo capture, AV | Production Lead | 21750 | 23200 | 6200 | 0 |  | In progress | Approve scope vs. guest privacy
B-10 | Protocol & Security | Advance, access control, medical standby, credential support | Protocol Lead | 34200 | 37600 | 18400 | 0 |  | At risk | Access-control scope requires decision
B-11 | Program Management | Program lead, producer, coordinator, onsite control room | Program Director | 43800 | 43800 | 21900 | 0 |  | In progress | Staffing finalizes after guest lock
B-12 | Contingency | Weather, schedule, and last-minute guest-service reserve | Program Director | 30500 | 35200 | 0 | 0 |  | Held | Release only with steering approval
TOTAL | [8 empty] | CONTROLLED | Fictional illustrative financial plan only.
Budget note: the dashboard and control worksheets are designed to show planning discipline. Actuals are intentionally set to $0 because this fictional event did not occur.

## 05 ¦ Budget Dashboard
FICTIONAL ILLUSTRATIVE CASE STUDY — SELF-INITIATED WORK SAMPLE — NOT A REAL EVENT, QUOTE, OR CLIENT ENGAGEMENT
Budget Dashboard
Visual control sheet using fictional planning figures from the Master Budget.
| PLANNED BUDGET |  | REFORECAST |  | COMMITTED | CONTINGENCY HELD
| Category | Plan | Reforecast | Committed | Variance
Guest Services
Venue & F&B
Accommodation
Transport
Experience Design
Content & Production
Protocol & Security
Program Management
Contingency

## 06 ¦ Vendor Directory
FICTIONAL ILLUSTRATIVE CASE STUDY — SELF-INITIATED WORK SAMPLE — NOT A REAL EVENT, QUOTE, OR CLIENT ENGAGEMENT
Vendor Directory
All companies and contacts are fictional placeholders created for this illustrative planning sample.
Workstream | Vendor Role | Fictional Company | Primary Contact | Scope | Commercial Model | Budget Owner | Critical Date | Status | Contingency / Plan B | RAG
Guest Services | Guest host staffing | Welcome Current | M. Rowan | Arrival desk, host team, guest comms | Day rates + retainer | Guest Services | Jul 2 | In progress | Hold 2 standby hosts | Amber
Venue & F&B | Welcome lunch | Harborline Table Co. | S. Chen | Private lunch, service, dietary protocol | Per-person + room fee | F&B Lead | Jun 30 | In progress | Second waterfront room held | Green
Venue & F&B | Signature dinner | Alder & Salt Events | J. Hale | Dinner, service, kitchen, private room | Minimum spend | F&B Lead | Jul 3 | In progress | Alternate format in same building | Amber
Accommodation | Host hotel | Watermark House | R. Diaz | Suites, day-use, meeting rooms, lobby coordination | Room block | Hotel Lead | Jun 21 | Complete | Secondary hold at partner hotel | Green
Transport | Executive transport | Northline Mobility | T. Brooks | SUVs, sprinters, airport protocol, standby | Hourly + mileage | Transport Lead | Jul 9 | In progress | Extra SUV on 90-min call | Green
Experience Design | Floral / tablescape | Petal & Pine Studio | L. Ames | Fresh florals, linen, arrival details | Design fee + rentals | Experience Design | Jul 5 | In progress | Seasonal substitution library | Amber
Production | Event production | Clearline Production | K. Soto | AV, discreet signage, cueing, power | Day rate + equipment | Production Lead | Jul 1 | Not started | Hotel house AV fallback | Amber
Protocol | Access control | Sentinel Guest Protocol | A. Young | Advance, access list, credential support | Day rate | Protocol Lead | Jul 8 | At risk | Reduce footprint to priority zones | Red
Medical | Medical standby | Sound Health Response | D. Finch | Event standby support | Daily flat rate | Protocol Lead | Jul 9 | Not started | Hotel EMT partner | Green
Content | Guest materials | Field & Folio | N. Reed | Briefing books, local guide, place cards | Project fee | Production Lead | Jun 25 | In progress | Digital brief fallback | Green
Program Management | Program office | Northwest Program Desk | G. Ellis | Producer, coordinator, control room | Retainer + onsite | Program Director | Jul 1 | Complete | Independent coordinator bench | Green
Guest Experience | Waterfront moment | Blue Hour Hospitality | P. Leung | Terrace, music cue, local guide, host moment | Project fee | Experience Design | Jul 10 | Not started | Indoor salon conversion | Amber

## 07 ¦ Master Timeline
FICTIONAL ILLUSTRATIVE CASE STUDY — SELF-INITIATED WORK SAMPLE — NOT A REAL EVENT, QUOTE, OR CLIENT ENGAGEMENT
Master Timeline
Illustrative planning cadence for a 10-week executive-delegation program.
ID | Workstream | Key Deliverable | Owner | Start | Due | Gate | Status | Dependency | Next Action | RAG
T-01 | Program Governance | Approve fictional case-study scope and principles | Program Director | 2026-05-04 | 2026-05-08 | G0 / Scope | Complete | None | Archive working brief | Green
T-02 | Guest Strategy | Define cohorts, guest hierarchy, executive hosts | Program Director | 2026-05-06 | 2026-05-15 | G1 / Audience | Complete | T-01 | Prepare relationship grid | Green
T-03 | Venue & F&B | Hold priority venue concepts and room options | F&B Lead | 2026-05-11 | 2026-05-29 | G2 / Format | In progress | T-02 | Shortlist 2 feasible formats | Amber
T-04 | Accommodation | Confirm suite / meeting room scenario | Hotel Lead | 2026-05-12 | 2026-05-27 | G2 / Format | Complete | T-02 | Release secondary hold | Green
T-05 | Experience Design | Develop welcome, tablescape, and guest-material concepts | Experience Design | 2026-05-18 | 2026-06-05 | G3 / Design | In progress | T-03 | Review concept deck | Amber
T-06 | Transport | Map guest movements and vehicle capacity | Transport Lead | 2026-05-25 | 2026-06-12 | G3 / Logistics | In progress | T-02 | Lock flight assumptions | Green
T-07 | Protocol | Draft access and privacy assumptions | Protocol Lead | 2026-06-01 | 2026-06-19 | G3 / Protocol | At risk | T-02 | Escalate access decision | Red
T-08 | Content | Create executive briefing-book outline | Content Lead | 2026-06-08 | 2026-06-22 | G4 / Briefing | Not started | T-02 | Gather executive inputs | Green
T-09 | Vendor Management | Issue fictional scopes and confirm lead times | Program Director | 2026-06-15 | 2026-06-29 | G4 / Commercial | Not started | T-03,T-05 | Complete vendor decision log | Amber
T-10 | Guest Services | Build arrival, preference, and host-assignment plan | Guest Services | 2026-06-22 | 2026-07-03 | G5 / Guest Readiness | Not started | T-02,T-06 | Validate sensitive needs handling | Green
T-11 | Run of Show | Draft minute-by-minute Day 2 control sheet | Producer | 2026-06-29 | 2026-07-08 | G5 / Operations | Not started | T-03,T-06,T-07 | Schedule tabletop review | Amber
T-12 | Risk Management | Review contingencies and decision gates | Program Director | 2026-07-06 | 2026-07-10 | G6 / Readiness | Not started | T-07,T-11 | Run 45-minute risk review | Red
T-13 | Executive Office | Confirm host briefings and speaking cues | Executive Office | 2026-07-08 | 2026-07-13 | G6 / Readiness | Not started | T-08,T-11 | Send briefing book v1 | Green
T-14 | Onsite Delivery | Final readiness call and operating handoff | Program Director | 2026-07-14 | 2026-07-15 | G7 / Go | Not started | All | Confirm final owner grid | Amber
T-15 | Post Program | Relationship and operational readout | Program Director | 2026-07-20 | 2026-07-24 | G8 / Learn | Not started | Program complete | Draft insights memo | Green

## 08 ¦ Run of Show
FICTIONAL ILLUSTRATIVE CASE STUDY — SELF-INITIATED WORK SAMPLE — NOT A REAL EVENT, QUOTE, OR CLIENT ENGAGEMENT
Day 2 Run of Show
Illustrative control sheet for the signature program day. Use as a project-management work sample, not a live event plan.
Call Time | Guest Time | Moment | Action / Detail | Primary Owner | Support | Guest Signal | Operational Check | Contingency | Status | RAG
06:30 | — | Control room open | Producer opens master log; weather, transport, guest changes reviewed | Producer | Program Director | Calm before first guest | All overnight changes entered | Use mobile control room if hotel space shifts | In progress | Green
07:00 | — | F&B / room check | Breakfast salon table, dietary cards, name cards, service pace reviewed | F&B Lead | Guest Services | No guest sees preparation | Service sequence confirmed | Move to library salon | In progress | Green
07:20 | — | Host briefing | Executive hosts receive 1-page relationship brief and day cues | Executive Office | Program Director | Hosts know why each conversation matters | Acknowledgement captured | Digital brief if print delayed | Complete | Green
07:40 | 08:00 | Executive breakfast arrival | Greet principals individually; seat by relationship objective | Guest Services | Executive Hosts | Expected, not processed | Guest count / seating reconfirmed | Use lounge overflow | In progress | Amber
08:00 | 08:10 | Opening framing | Chief host gives concise welcome and day orientation | Chief Host | Content Lead | Warm confidence, no over-explaining | Remarks + microphone checked | Informal hosting if AV fails | Not started | Green
08:15 | 08:50 | Breakfast conversation | Service maintains discreet pace; host notes priority interactions | F&B Lead | Guest Services | Room feels easy, not staged | Dietary / timing / side conversations | Extend vehicle hold | Not started | Green
09:00 | 09:30 | Transition to roundtable | Vehicles staged; guest escort and route sequencing | Transport Lead | Guest Services | No waiting, no crowding | Vehicle load / weather / route confirmed | Indoor route / buffer time | Not started | Amber
09:45 | 10:00 | Roundtable pre-set | Moderator, materials, water, name placement, note capture | Content Lead | Producer | Intentional, executive-ready room | Attendance and seating verified | Shorten layout / use standing start | Not started | Green
10:00 | 11:20 | Innovation roundtable | Moderated discussion; producer holds pace; notes capture themes | Program Sponsor | Producer | Substantive, participant-centered conversation | Time cues, privacy, speaker balance | Shift to smaller breakout | Not started | Green
11:20 | 11:30 | Transition / reset | Clear room; discreet guest escort; prepare vehicles | Guest Services | Transport Lead | Energy stays intact | Guest movement reconciliation | Hold guests in hospitality lounge | Not started | Green
11:45 | 12:15 | Market lunch arrival | Host welcomes group; seasonal menu and Seattle cue introduced | F&B Lead | Experience Design | Local, generous, easy | Seating / menu / photo rules | Indoor private table | Not started | Amber
12:15 | 13:15 | Hosted lunch | Table captain maintains pacing; note guest interest areas | Executive Host A | Guest Services | Conversation feels naturally curated | Meal timing / guest comfort | Compress dessert if behind | Not started | Green
13:30 | 14:20 | Relationship windows set | Principals move to selected suites for 1:1s | Executive Office | Guest Services | Private, precise, protected time | Meeting grid and escort handoff | Reassign rooms / hold lounge | Not started | Red
14:30 | 16:00 | One-to-one meetings | Track start/end and next-step owner in secure internal log | Executive Hosts | Program Director | Business value is advanced quietly | Timing / access / privacy | Move conversation to alternate salon | Not started | Amber
16:00 | 17:10 | Reset / guest downtime | Hotel provides privacy; production converts terrace experience | Producer | Hotel Lead | Guests have space before evening | Weather, florals, sound level | Indoor salon setup | Not started | Green
17:30 | 18:45 | Waterfront moment | Terrace welcome, floral arrival, local guide, sunset timing | Experience Design | Guest Services | Seattle feels personal and memorable | Weather / guest mobility / sound | Indoor windowside experience | Not started | Amber
19:00 | 19:20 | Signature dinner arrival | Place-card escort, welcome beverage, seat confirmation | Guest Services | F&B Lead | Every guest is recognized immediately | Final seating / protocol / gifts | Re-seat using fallback chart | Not started | Green
19:30 | 21:45 | Hosted dinner | Course cadence, remarks, priority interactions, discreet issue management | Program Director | F&B Lead | The evening feels effortless because operations are invisible | Service / speech / security / timing | Skip formal remarks / adjust pacing | Not started | Green
21:45 | 22:30 | Departure protocol | Vehicle waves, luggage notes, host goodbyes, last guest confirmed | Transport Lead | Guest Services | Warm closure with no loose ends | Vehicle / guest reconciliation | Hold final vehicle / hotel lounge | Not started | Green
22:45 | — | End-of-day readout | 15-minute staff review; decisions and guest signals logged | Program Director | All workstream leads | Learning is captured while fresh | Update risks / next day changes | Escalate material issue by 23:15 | Not started | Green

## 09 ¦ RACI & Workstreams
FICTIONAL ILLUSTRATIVE CASE STUDY — SELF-INITIATED WORK SAMPLE — NOT A REAL EVENT, QUOTE, OR CLIENT ENGAGEMENT
RACI & Workstreams
Illustrative ownership model. R = Responsible ¦ A = Accountable ¦ C = Consulted ¦ I = Informed.
ID | Decision / Deliverable | Program Director | Executive Office | Guest Services | F&B / Hotel | Experience Design | Transport / Protocol | Content / Production | Steering Group | Control Note
R-01 | Approve program purpose and stakeholder outcomes | A | C | I | I | I | I | I | C | Confirm before any guest-facing planning
R-02 | Confirm guest cohorts and executive host assignments | R | A | C | I | I | I | I | C | Relationship priority drives staffing
R-03 | Set service format and guest journey | A | C | R | C | R | I | C | I | Document what each guest should feel
R-04 | Select venues / hotel configuration | A | I | C | R | C | I | I | C | Protect privacy and travel time
R-05 | Approve budget reforecast over $7,500 | R | C | I | C | C | C | C | A | Record option, impact, recommendation
R-06 | Lock transportation and arrival protocol | A | I | C | I | I | R | I | I | Use flight updates as primary trigger
R-07 | Approve access-control and privacy plan | A | C | I | I | I | R | I | C | Clarify escalation owner
R-08 | Develop executive briefing material | C | A | I | I | I | I | R | I | Keep to one actionable page per host
R-09 | Final guest seating and rooming plan | A | C | R | C | C | I | I | I | Change control after final lock
R-10 | Signature dinner run of show | A | C | C | R | C | C | C | I | Producer owns live pace
R-11 | Weather contingency decision | A | I | C | C | R | C | C | I | Call timing determined 6 hours prior
R-12 | Live issue escalation | A | I | R | C | C | C | C | I | Use control room log
R-13 | Post-program readout and next steps | A | C | C | C | C | C | R | I | Name owner + deadline for each action

## 10 ¦ Guest Matrix
FICTIONAL ILLUSTRATIVE CASE STUDY — SELF-INITIATED WORK SAMPLE — NOT A REAL EVENT, QUOTE, OR CLIENT ENGAGEMENT
Guest Matrix
No personal data is included. These are fictional guest cohorts and planning attributes only.
Cohort ID | Fictional Guest Cohort | Relationship Objective | Priority Moments | Host / Owner | Personalization Thought-Starter | Access / Mobility Notes | Arrival | Day 2 | Departure | Status
G-01 | Delegation principals | Establish senior relationship confidence | Arrival, salon dinner, 1:1s, signature dinner | Executive host A | Local guide with interests surfaced in advance | Private vehicle, lounge buffer, step-free options | Individual welcome | Protected conversation windows | Host-led goodbye | In progress
G-02 | Senior partner leaders | Advance partnership themes | Roundtable, market lunch, signature dinner | Program sponsor | Conversation note tailored to shared agenda | Venue access, discreet arrival | Partner welcome | Roundtable seating | Next-step owner assigned | In progress
G-03 | Accompanying family members | Create comfort and local orientation | Neighborhood welcome, terrace moment | Guest host | Curated local options, flexible pacing | Mobility / dietary preferences captured conceptually | Separate welcome support | Optional hosted experience | Direct transport support | Not started
G-04 | Internal executive hosts | Ensure confident hosting and clear priorities | Breakfast briefing, 1:1s, dinner remarks | Executive Office | One-page relationship brief, role cues | Executive schedule and comms protocol | Briefed before arrival | Decision support on call | Readout participation | Complete
G-05 | Program delivery team | Make operations invisible to guests | All transitions, control room, end-of-day readout | Program Director | Clear owner grid, issue escalation path | Back-of-house access protocol | Staged 90 minutes early | Shift schedule active | Final reconciliation | In progress

## 11 ¦ Risk & Decisions
FICTIONAL ILLUSTRATIVE CASE STUDY — SELF-INITIATED WORK SAMPLE — NOT A REAL EVENT, QUOTE, OR CLIENT ENGAGEMENT
Risk & Decision Log
A senior-ready view of the issues that need visibility, ownership, and a documented response.
Type | ID | Risk / Decision | Likelihood | Impact | RAG | Mitigation / Options | Owner | Decision Due | Status | Escalation Note
Risk | RISK-01 | Weather affects the outdoor waterfront moment | Medium | High | Amber | Hold indoor salon; call 6 hours prior; preserve guest flow regardless | Experience Design | Jul 17 | In progress | Senior host informed only if format changes
Risk | RISK-02 | Arrival timing shifts due to flight movement | Medium | High | Amber | Keep 45-minute buffer; standby host and vehicle; communicate through control desk | Transport Lead | Jul 16 | In progress | Update principal host immediately
Risk | RISK-03 | Access-control scope expands late | Medium | High | Red | Define priority zones; identify cost / guest-experience tradeoff; seek steering decision | Protocol Lead | Jun 19 | At risk | Escalate with 2 options and $ impact
Risk | RISK-04 | Dietary / cultural need discovered after menu lock | Low | Medium | Green | Maintain adaptable chef options and guest-service check-in at arrival | F&B Lead | Jul 10 | Not started | No escalation unless principal affected
Decision | DEC-01 | Choose signature dinner format: private dining room vs. terrace | — | High | Amber | Recommend private dining room with terrace welcome for weather resilience | Program Director | Jun 29 | In progress | Decision affects production and guest movement
Decision | DEC-02 | Approve fictional budget reforecast for protocol workstream | — | High | Red | Approve $3,400 increase or reduce scope to priority access zones | Steering Group | Jun 19 | At risk | Requires documented choice
Decision | DEC-03 | Confirm guest-photo and privacy posture | — | Medium | Amber | Recommend no guest photography unless consent process is defined | Content Lead | Jul 1 | Not started | Protects guest trust and avoids scope ambiguity
Decision | DEC-04 | Lock preferred gift / local guide format | — | Low | Green | Recommend useful Seattle orientation set, not branded merchandise | Guest Services | Jun 20 | In progress | Ensure production lead time

## 12 ¦ Comms Cadence
FICTIONAL ILLUSTRATIVE CASE STUDY — SELF-INITIATED WORK SAMPLE — NOT A REAL EVENT, QUOTE, OR CLIENT ENGAGEMENT
Communications Cadence
Illustrative governance rhythm for decision quality, guest confidence, and cross-functional delivery.
Cadence | Forum | Audience | Purpose | Inputs | Outputs / Decision Record | Owner | Start | End | Status
Weekly | Program leadership review | Program Director, workstream leads | Review RAG, decisions, budget, dependencies | Timeline, risk log, vendor status | Decision log and actions within 24 hours | Program Director | May 8 | Jul 10 | In progress
Bi-weekly | Steering checkpoint | Executive Office, program sponsor, director | Confirm purpose, relationship priorities, scope changes | Executive summary, financial dashboard | Leadership decisions / escalation notes | Executive Office | May 15 | Jul 10 | In progress
Weekly | Guest readiness huddle | Guest Services, transport, hotel, F&B | Review arrival, preferences, hosts, transitions | Guest matrix, itinerary, transport grid | Updated guest readiness list | Guest Services | Jun 19 | Jul 15 | Not started
Daily / Event | Control room pulse | All onsite workstream leads | Confirm current state and immediate risks | Run of show, live changes, weather | 15-minute live decision log | Producer | Jul 16 | Jul 18 | Not started
Post-program | Relationship readout | Executive hosts, program team | Capture guest signals and follow-through | Host notes, meeting outcomes, issue log | Named next steps and learning memo | Program Director | Jul 20 | Jul 24 | Not started
Suggested Portfolio Caption
Use this only with the fictional disclosure visible.
Illustrative Seattle Executive Delegation Case Study — a self-initiated program-management work sample demonstrating how I structure executive hospitality, program delivery, financial controls, guest experience, and decision readiness. All names, dates, pricing, vendors, and event details are fictional.